## Portfolio Management
This worksheet is designed to help compile an inventory of projects in a program, a portfolio, a department, or an entire organization. If a project in the inventory does not have a plan, schedule, or budget, it may be difficult to fill out all the columns below. In this case, meet with the person responsible for the project to get as much information as possible and note in columns when information is not available. If it is difficult for project managers to answer the simple questions in this inventory, it is likely that the project is not being managed effectively. Inventories can be useful in the following circumstances: 1. When senior management wants a concise list of projects in a program, portfolio, or organization. 2. When senior management must choose among proposed projects that are competing for funding and wants a high level view of all projects being proposed.
No | Project Name | Project Goal | Schedule |  | Current Phase | Costs |  | Key Resources | Major Risks
|  |  | Start Date mm.dd.yy | End Date mm.dd.yy |  | Spent To Date (QAR) | Total Project Cost (QAR) | Names | Risk Event Statement | Impact H/M/L | Probability H/M/L
Provide a project number | Enter the official project name | Enter the project goal | Enter project start date | Enter project finish date | Describe the current phase of work | Enter budget spent to date | Enter total budget for project | List names and titles for key positions | Provide risk event statement, but only for the most significant risks | Enter estimate for impact and probability as high, medium, or low
Example:
1 | Road Safety Promotion Project | To reduce road accidents | 12.01.04 | 12.01.06 | Finishing a public awareness campaign re (i) how to drive safely and (ii) new stricter laws for speeding and reckless driving. Team will begin closing the project in 2 months | 3500000 | 4000000 | Project Sponsor, Secretary General | Public awareness campaign may have trouble competing with Asian Games promotions happening at the same time | H | H
[8 empty] | Project Manager, Mohammed Muktar | Market firm is from the UK, and the cost of the project may increase if the exchange rate changes | M | M
1
2
3
4
5
6