## Issues
This log is used to record and track project issues. Issues are things that are currently happening that require resolution for the project to proceed successfully. This log includes all issues identified over the life of the project, including those that are resolved and those that are still active. Do not delete issue information from this log: it is a permanent record of project issues. Tips: 1. Create your first Issue Log when the Project Plan is approved, using the issue section of the Project Plan as initial content. 2. Change the title of this document by clicking "View" in the Tools Menu and selecting "Header and Footer" and then "Custom Header". 3. Active issues in a period should be recorded in the Project Status Report for that period according to the thresholds for reporting issues in the Issue Management Plan. 4. Identifying new issues and updating this log should be part of an ongoing risk management process with clear roles and responsibilities. See the Issue Management Plan Template for suggestions on these. 5. Each issue should be assigned a number as a unique identifier (see left hand column) that does not change over the life of the project and that is also used on the Project Status Report, Issue Identification Form, and Issue Assessment Form. 6. There should be specific defintions for the terms high, medium, and low. See the Issue Management Plan for suggested definitions. 7. Issues are things that are currently happening that can affect the project. If the situation has not yet occured, it should be assessed as a possible risk.
1. BASIC ISSUE INFORMATION |  |  |  |  | 2. ISSUE ASSESSMENT INFORMATION |  |  | 3. ISSUE RESPONSE INFORMATION
Issue Number | Issue Description | Responsible | Date Reported day-month-year | Last Update day-month-year | Impact H / M / L | Impact Description | Status Resolved / Not Resolved | Completed Actions | Planned Future Actions
Provide unique identifier to issue | Describe the issue by saying what is happening or what has happened and how it is negatively impacting the project | Name or title of team member responsible for issue | Enter the date the issue was first reported | Enter the date the issue (not the entire log) was updated | Enter here H (High); M (Medium); or L (Low) according to impact definitions | List the specific impact the issue is expected have on the project schedule, budget, scope, and quality. Other impacts can also be listed | State whether or not the issue has been resolved or if further action is required | List, by date, all actions taken to respond to the issue. This does not include assessing the issue | List what will be done in the future to respond to the issue
Example I 1 | Member of the design team has a computer virus which has destroyed project files, creating the need for rework and project delays | Design Team Lead | 2005-12-14 | 2005-12-30 | M | Timeline -- rework is expected to take 3 weeks Cost -- rework is expected to cost QAR 40,000 Scope -- none Quality -- none | Resolved | 14-Dec-2005: Additional resources found to assist with re-creating lost deliverables 15-Dec-2005: Entire team reminded of the importance of following the document management process to prevent loss of files: Admin Assistant reviewed work backed up on server to identify any teams that have not been backing up files properly and will do weekly checks for remainder of project 20-Dec-2005: Project Manager shifted budget from contingency to Design Team to cover rework costs. Note that the contingency budget is now significantly diminished | N / A -- Issue is resolved
Example I 2 | Key supplier has declared bankrupcy, creating the need to find a new supplier which will cause schedule delays | Project Manager | 2006-03-25 | 2006-03-25 | H | Timeline -- delay is expected to be 3 months Cost -- delay is expected to cost 20% of project budget Scope -- team must repeat procurement and contract negotiation activities Quality -- none. Other suppliers in the market provide services of equal quality to former supplier | Not Resolved | 12-Jan-2006: Met with supplier to discuss options 15-Jan-2006: Spoke with other suppliers regarding availability 20-Jan-2006: Prepared contingency plan and RFP in case supplier goes bankrupt 25-March-2006: Moved risk to issue process -- supplier lost lawsuit and declared bankrupcy | 30-March-2006: Enacting Contingency Plan, which involves stopping the project for 3 months to finalize procurement and get new supplier started. Having a Contingency Plan and RFP written reduced impact from a 6 month delay to a 3 month delay
I 1
I 2
I 3
I 4
I 5
I 6
I 7
I 8
I 9
I 10
I 11
I 12
I 13
I 14
I 15
I 16
I 17
I 18
I 19
I 20
I 21
I 22
I 23
I 24
I 25
I 26
I 27
I 28
I 29
I 30
I 31
I 32
I 33
I 34
I 35
I 36
I 37
I 38
I 39
I 40
I 41
I 42
I 43
I 44
I 45
I 46
I 47
I 48
I 49
I 50
I 51
I 52
I 53
I 54
I 55
I 56
I 57
I 58
I 59
I 60
I 61
I 62
I 63
I 64
I 65
I 66
I 67
I 68
I 69
I 70
I 71
I 72
I 73
I 74
I 75
I 76
I 77
I 78
I 79
I 80
I 81
I 82
I 83
I 84
I 85
I 86
I 87
I 88
I 89
I 90
I 91
I 92
I 93
I 94
I 95
I 96
I 97
I 98
I 99
I 100