## Schedule
Add columns to this section as needed -- each team member should have their own column
| The information in this column will come from your work breakdown structure |  |  | Project Team Level of Effort in WEEKS |  |  |  | Add columns to this section as needed to cover length of project. You can have a daily, weekly, monthly, or quarterly view.
|  |  |  | Internal |  | External
No | Summary Tasks and Work Packages | Precedents | Duration in WEEKS | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
1 | Example summary task | bar: Week 1 to Week 2
1.1 | work package |  | 1 | 1 | bar: Week 1
1.2 | work package | 1.1 | 0.5 |  | 1 | bar: Week 2
1.3 | work package | 1.1, 1.2 | 3 |  |  | 1 | 2 | bar: Week 3 to Week 5
1 | Summary Task 1 | bar: Week 1 to Week 2
1.1 | work package
1.2 | work package
1.3 | work package
2 | Summary Task 2 | bar: Week 1
2.1 | work package
2.2 | work package
2.3 | work package
3 | Summary Task 3 | bar: Week 1
3.1 | work package
3.2 | work package
3.3 | work package
Add rows as needed -- each work package should have its own row
| Total Level of Effort |  |  | 1 | 1 | 1 | 2 | bar: Week 1