## Sheet1
Prepared By:
Date:
Risk Number | Risk Event Statement | Risk Score This Time | Risk Score Last Time | Weeks on Risk Status Report | Status of Response N / P / PE / EE | Responsible | Description of Response Activities
Provide a unique identifier for risk | A risk event statement states (i) what might happen in the future and (ii) its possible impact on the project. "Weather" is not a risk event statement. "Bad weather may delay the project" is a risk event statement. | Taken from updated Risk Analysis Worksheet | Taken from previous Risk Status Report | Enter the date the risk (not the entire log) was updated | Enter here N (No Plan); P (Plan but not enacted); PE (Plan enacted but effectiveness not yet known); EE (Plan enacted and effective) | Enter name or title of team member responsible for risk | List, by date, all actions taken to respond to the risk. This does not include assessing the risk
Example R 1 | Concrete prices may increase, causing the project to go over budget | 15 | 30 | 2006-01-12 | PE | Materials Acquisitions Manager | 10-Jan-2006: Asked concrete supplier to guarantee a price; request denied
R 1
R 2
R 3
R 4
R 5
R 6
R 7
R 8